## Sheet1
Task Name | Start | End | Duration (days)
Design System Architecture | 2025-07-01 | 2025-07-02 | 1
Create Database Schema | 2025-07-01 | 2025-07-03 | 2
Write Hardware & Software Design | 2025-07-02 | 2025-07-04 | 2
Complete Duration Estimate (DOC) | 2025-07-03 | 2025-07-04 | 1
Collaborate on Gantt Chart | 2025-07-04 | 2025-07-05 | 1
Flowchart / System Diagram Design | 2025-07-04 | 2025-07-04 | 1
Design and Implementation of Front-End Interface | 2025-06-24 | 2025-07-01 | 7
User Interface Styling | 2025-06-27 | 2025-07-02 | 5
Debugging Front-End Issues | 2025-07-01 | 2025-07-03 | 2
Contribution to Design Document | 2025-07-04 | 2025-07-05 | 1
Front-End System Architecture Diagram | 2025-07-04 | 2025-07-05 | 1
Google Sign in Integration | 2025-07-02 | 2025-07-04 | 2